## Agency Readiness Tasks Calendar
Core-CT Agency Readiness Task Calendar
Status | Item # | Description | Agency Response Type | Purpose | Project Area/Module | Start Date | End Date | Sam | Rich | Sam | Tom | Betty | Carolyn | Carolyn | Sam | Betty | Sam | Carolyn | Tom | Tom | Tom | Tom | Rich | Sam | Rich | Carolyn | Betty | Rich | Rich | Rich | Betty | Carolyn | Betty | Tom | Sam | Tom | Rich | Betty | Carolyn | Sam | Betty | Tom | Carolyn | Tom | Rich | Sam | Sam | Sam | Tom | Sam | Betty | Carolyn | Rich | Carolyn | Carolyn | Betty | Tom | Carolyn | Betty | Betty | Sam
[8 empty] | Administrative Services, Dept of | Agricultural Experment Station | Agriculture, Dept of | Attorney General, Office of | Auditors of Public Accounts | Banking, Dept of | Board of Regents for Dept of Higher Ed | Chief Medical Examiner | Children & Families, Dept of | Claims Commissioner, Office of the | Comptroller, Office of the State | CT Development Authority | CT Housing Finance Authority | CT Innovations | CT Lottery Corporation | CT Siting Council | Consumer Protection, Dept of | Correction, Dept of | Criminal Justice, Division of | Developmental Services, Dept of | Economic & Community Dev, Dept of | Education, State Dept of | Emergency Services & Public Protection, CT Dept of | Energy and Environmental Protection, Dept of | Financial & Academic Affairs for Higher Ed, Office of | Governmental Accountability, Office of | Health Care Advocate, Office of the | Human Rights & Opportunities, Commission on | Insurance, Dept of | Judicial Dept. | Labor, Dept of | Legislative Management, Office of | Library, State | Mental Health & Addiction Services | Military Dept. | Motor Vehicles, Dept of | Policy & Management, Office of | Probate Court Administration | Properties Review Board | Protection & Advocacy for Persons with Disabilities, Office of | Public Defender, Office of the Chief | Public Health, Dept of | Rehabilitation Services, Bureau of | Revenue Services, Dept of | Secretary of State, Office of the | Social Services, Dept of | Soldiers, Sailors & Marines Fund | Teachers Retirement Board | Transportation, Dept of | Treasurer, Office of the State | UCONN | UCONN Health Center | Veterans Affairs, Dept of | Workers' Compensation Commission
1 - PeopleTools Upgrade
Complete | 1-1 | Browser & OS Compatability | Confirmation email | Agencies will ensure the compatibility of their browsers for Core-CT use. | All | 2012-02-28 | 2012-03-22 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Complete | 1-2 | PeopleTools Upgrade Documentation Distribution | Confirmation email | Agencies will confirm the distribution of the PeopleTools Upgrade documentation to end users as an awareness of the aesthetic changes. | All | 2012-02-28 | 2012-03-22 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
2 - HCM
2-1
3 - Financials
3-1
4 - User Acceptance Testing
4-1
5 - Training
5-1

## Assignment Status (hidden)
SWIFT AGENCY ASSIGNMENT CALENDAR
Category | Item # | Description | Start Date | Duration | Due Date | Team Responsible for Dissemenation | Number of Agencies Included | Number of Agencies Responded | Number of Agencies Not Responded | % Complete | B7P | G02 | G9K | B04 | B9D | B14 | B7E | E50 | G9N | G06 | B15 | B11 | H7X | G9L | H7Q | G45 | G9J | G9X | G9M | H7H | B7G | B13 | P78 | J58 | H7F | H7U | G9Y | E37 | H7S | B22 | B20 | E44 | G09 | G39 | H12 | E9W | B34 | G17 | H55 | E95 | G19 | G38 | B43 | J70 | B42 | L49 | L5D | L10 | L10 | G03 | H7M | H7B | P01 | G10 | G62 | E25 | G05 | E26 | R29 | H7C | H7K | G46 | E60 | H9G | G92 | H7J | P7T | H7D | H7W | R32 | B7S | H7V | J52 | G63 |  | P07 | B82 | G67 | G53 | P9E | H7L | G61 | J65 | J68 | G69 | T79 | J33 | H75 | H7R | R9P | B41 | E77
[11 empty] | Accountancy Board | Administration | Administrative Hearings | Agriculture | Amateur Sports | Animal Health Board | Architecture, Engineering, Land Surveying and Landscape | Arts Board | Asian-Pacific Council | Attorney General | Barber Examiners Board | Barber/Cosmetologist Examiners | Behavioral Health & Therapy Board | Black Minnesotans | Board of Podiatric Medicine | Bureau of Mediation Services | Campaign Finance Board | Capitol Area Architectural & Planning Board | Chicano Latino Affairs Council | Chiropractor Boards | Combative Sports Commission | Commerce | Corrections | Court of Appeals | Dentistry Board | Dietetics & Nutrition Practices Board | Disability Council | Education | Emergency Medical Services Board | Employment & Economic Development | Explore Minnesota Tourism | Faribault Academies | Gambling Control Board | Governor’s Office | Health | Higher Education Facilities Authority | Housing Finance Agency | Human Rights | Human Services | Humanities Commission | Indian Affairs Council | Investment Board | Iron Range Resources and Rehabilitation Agency (IRRRA) | Judicial Standards Board | Labor & Industry | Legislative Auditor | Legislative Coordinating Commission | Legislature - House | Legislature - Senate | Lottery | Marriage & Family Therapy Board | Medical Practices Board | Military Affairs | Minnesota Management & Budget | Minnesota State Retirement System (MSRS) | MN Center for Arts Education | MN Racing Commission | MN State Colleges & Universities (MnSCU) | Natural Resources (DNR) | Nursing Board | Nursing Home Administrators Board | Office of Enterprise Technology | Office of Higher Education | Ombudsman Mental Health & Dev Dis | Ombudsperson for Families | Optometry Board | Peace Officers Standards & Training Board (POST) | Pharmacy Board | Physical Therapy Board | Pollution Control Agency | Private Detective Board | Psychology Board | Public Defense Board | Public Employees Retirement Association (PERA) | Public Facilities Authority | Public Safety | Public Utilities Commission | Revenue | Secretary of State | Sentencing Guidelines Comission | Social Work Board | State Auditor | Supreme Court | Tax Court | Teachers Retirement Association (TRA) | Transportation | Trial Court | Veterans Affairs | Veterinary Medicine Board | Water & Soil Resources Board | Workers' Compensation Court of Appeals | MN - Zoological Garden
1 - Requirements, Fit and Design Sessions
| 1 - 1 | Grant Security (Pre-Award) | 2010-01-01 | 12 weeks |  |  | 0 | 0 | 0 | #DIV/0! | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
2 - Configuration Data Gathering
| 2 - 1 | Agency-Specific ChartField Mappings | 2010-03-01 | 12 weeks |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 2 - 2 | Inventory Definitions and Inventory Locations Survey | 2010-03-01 | 12 weeks |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 2 - 3 | Identify Address Location | 2010-03-01 | 12 weeks |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 2 - 4 | Validate list of Buyer/Contract Officer Information | 2010-03-01 | 12 weeks |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 2 - 5 | Indirect Cost Rates | 2010-03-01 | 12 weeks |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 2 - 6 | Project Costing/Grant ChartField Structure | 2010-03-01 | 12 weeks |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 2 - 7 | Grant Information - Grant titles and Grantors for an award | 2010-03-01 | 12 weeks |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 2 - 8 | Grant Expenditure/Revenue Budget Control Structure | 2010-03-01 | 12 weeks |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 2 - 9 | Complete Billing Conversion Survey | 2010-03-01 | 12 weeks |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 2 - 10 | Complete Listing of Bill/Debt Types and Distribution Codes Survey | 2010-03-01 | 12 weeks |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 2 - 11 | Review and Determine Cost Allocation | 2010-03-01 | 12 weeks |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 2 - 12 | Document Management Survey | 2010-04-01 | 8 weeks |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 2 - 13 | Gather ChartField values for Speed Charts | 2010-04-01 | 8 weeks |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
3 - Interface Design, Development & Testing
| 3 - 1 | Validate interface inventories | 2010-04-01 | 11 months |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 3 - 2 | Prepare Interface Development Team | 2010-04-01 | 11 months |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 3 - 3 | Review current systems and data elements in existing non data warehouse interfaces | 2010-04-01 | 11 months |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 3 - 4 | Receive, Review and Understand Interface Data Mapping | 2010-06-01 | 11 months |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 3 - 5 | Ensure Agency Applications accommodate SWIFT Interfaces | 2010-06-01 | 11 months |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 3 - 6 | Verify testing environment connectivity to SWIFT for major testing cycles and Go-Live | 2010-08-01 | 11 months |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 3 - 7 | Participate in Interface Development Testing for major testing cycles | 2010-08-01 | 11 months |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 3 - 8 | Prepare Agency Systems for SWIFT Go-Live | 2011-03-01 | 4 months |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
4 - Conversion Data Gathering
| 4 - 1 | Complete Conversion Update for Accounts Receivable open items | 2010-05-10 | 8 weeks with periodic updates to follow |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 4 - 2 | Asset Conversion Survey | 2010-05-10 | 8 weeks with periodic updates to follow |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 4 - 3 | Conversion Mapping Validation | 2010-05-10 | 8 weeks with periodic updates to follow |  |  | 0 | 0 | 0 | #DIV/0! | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| 4 - 4 | Map Chart of Accounts in Agency specific systems to SWIFT | 2010-05-10 | 8 weeks with periodic updates to follow |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 4 - 5 | Obtain Inventory & Item extract sources as soft copies, complete field mapping and cleanup | 2010-05-10 | 8 weeks with periodic updates to follow |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 4 - 6 | Complete Grants Conversion Survey | 2010-05-10 | 8 weeks with periodic updates to follow |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 4 - 7 | Capital/Agency Directed Projects | 2010-05-10 | 8 weeks with periodic updates to follow |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 4 - 8 | Validate Contracts for Conversion Purposes | 2010-05-10 | 8 weeks with periodic updates to follow |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
5 - Data Warehouse (EPM) Development & Testing
TBD
6 - Business Process Readiness Planning | [6 empty] | 0 | 0 | 0 | #DIV/0!
| 6 - 1 | Business Process Implementation Planning | 2010-06-23 | 12 weeks | [6 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
7 - Security Role Mapping | [6 empty] | 0 | 0 | 0 | #DIV/0!
| 7 - 1 | Initial Security Role Mapping | 2010-07-01 | 12 weeks |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 7 - 2 | Final Security Role Mapping | 2011-04-01 | 4 weeks | [6 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
8 - Business Process Readiness Execution | [6 empty] | 0 | 0 | 0 | #DIV/0!
| 8 - 1 | Business Process Implementation Execution | 2010-10-01 | 9 months |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
9 - Agency Readiness Assessment
| 9 - 1 | Agency Readiness Assessment | 2010-11-02 | 8 months |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
10 - End-User Training
| 10 - 1 | Job Task Survey | 2010-01-07 | 7 weeks | 2010-03-01 | ER | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 10 - 2 | Agency Supplemental Training Material | 2010-11-01 | 12 weeks |  |  | 0 | 0 | 0 | #DIV/0! | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| 10 - 3 | Train-the-Trainer (TTT) Workshops | 2011-01-01 | 8 weeks |  |  | 0 | 0 | 0 | #DIV/0! | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
| 10 - 4 | End User Training Enrollment | 2011-02-01 | 5 months |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| 10 - 5 | End-User Training | 2011-03-01 | 4 months |  |  | 92 | 0 | 92 | 0% | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
11 - Functional Testing
| 11 - 1 | User Acceptance Testing | 2011-03-11 | 4 weeks | [6 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
|  | Total Number of Assignments: |  |  |  |  | Total Number of Agencies Included in Assignments: | Total Number of Agencies Responded: | Total Number of Agencies Not Responded: | Total Percent Complete:
|  | 35 |  |  |  |  | 3128 | 0 | 3128 | 0%
Note on CH3: MMB: Unable to locate an Agency Code for this organization.